## Sheet1
Project Summary Cost
|  | Labor Total |  | 11856
|  | Furniture Total |  | 46780
|  | Project Total |  | 58636
Labor Costs
Hourly Rate
|  | Shwet Jain |  |  | 55
|  | Carly Jones |  |  | 46
|  | Rocco Santaro |  |  | 42
|  | Michelle Phillips |  |  | 44
|  | Peter Buckley |  |  | 41
|  | Average |  |  | 45.6
|  | Time(hrs) | Hourly Rate | Approx Cost
Initiating the project
Establish Project Charter |  | 6 | 45.6 | 273.6
Conference Room Meeting |  | 3 | 45.6 | 136.8
Warehouse Site Survey |  | 4 | 45.6 | 182.4
Review Initiation phase |  | 6 | 45.6 | 273.6
Planning Project
Design Furniture Layout |  | 3.5 | 45.6 | 159.6
Hardware/Software Specification of the PC's |  | 3.5 | 45.6 | 159.6
VoIP Handset Selection |  | 3 | 45.6 | 136.8
Specify Printer |  | 3 | 45.6 | 136.8
Ubiquiti wireless access points selection |  | 4 | 45.6 | 182.4
Cat 6e cable Selection |  | 1 | 45.6 | 45.6
Ciena 5150 switch selection |  | 4 | 45.6 | 182.4
Execute Project
Order Furniture |  | 0.5 | 45.6 | 22.8
Order PC's |  | 0.5 | 45.6 | 22.8
Order VoIP handsets |  | 1 | 45.6 | 45.6
Order Printer |  | 1 | 45.6 | 45.6
Order Ubiquiti wireless access points |  | 1.5 | 45.6 | 68.4
Order Cat 6e cable |  | 1 | 45.6 | 45.6
Order Ciena 5150 cable |  | 2 | 45.6 | 91.2
Received and inspect furniture |  | 8 | 45.6 | 364.8
Received PC's |  | 2 | 45.6 | 91.2
Received and inspect VoIP handset |  | 1 | 45.6 | 45.6
Received Printer |  | 2 | 45.6 | 91.2
Received Ubiquiti wireless access points |  | 1 | 45.6 | 45.6
Received Cat 6e cable |  | 1.5 | 45.6 | 68.4
Received Ciena 5150 cable |  | 1 | 45.6 | 45.6
Create a Financial Plan |  | 15 | 45.6 | 684
Create Quality Plan |  | 20 | 45.6 | 912
Create a change management plan |  | 10 | 45.6 | 456
Create Risk Plan |  | 10 | 45.6 | 456
Review Planning phase |  | 10 | 45.6 | 456
Install cubical furniture |  | 8 | 45.6 | 364.8
Install PC's |  | 3 | 45.6 | 136.8
Install VoIP handsets |  | 4 | 45.6 | 182.4
Install Printer |  | 4 | 45.6 | 182.4
Install Ubiquiti wireless access points |  | 3 | 45.6 | 136.8
Install Cat 6e cable |  | 4 | 45.6 | 182.4
Install Ciena 5150 cable |  | 5 | 45.6 | 228
Integrate VoIP handsets with VoIP PBX |  | 4 | 45.6 | 182.4
Integrating PC's |  | 10 | 45.6 | 456
Connection between cables and switches |  | 6 | 45.6 | 273.6
Testing PC's for software/hardware issues |  | 8 | 45.6 | 364.8
Testing VoIP handsets and its connection |  | 4 | 45.6 | 182.4
Testing the functionality of the printer |  | 3 | 45.6 | 136.8
Testing the Ubiquiti access points |  | 5 | 45.6 | 228
Test Ciena 5150 and Cat 6e cable connection |  | 5 | 45.6 | 228
Review Testing Phase |  | 4 | 45.6 | 182.4
Closing Project
Seek Sponsor Approval |  | 6 | 45.6 | 273.6
Fix Open items |  | 12 | 45.6 | 547.2
Exit Surveys |  | 3 | 45.6 | 136.8
Create Archive Documents |  | 6 | 45.6 | 273.6
Close Contracts |  | 5 | 45.6 | 228
Pay-off Vendors |  | 6 | 45.6 | 273.6
Lessons Learnt |  | 6 | 45.6 | 273.6
Reassigning Resources |  | 3 | 45.6 | 136.8
Review Closing Phase |  | 3 | 45.6 | 136.8
Labor Total |  |  |  | 11856
Work hours total |  |  |  | 260
Item | Unit Price | No.of Units | Total
Cubical furniture | 1575 | 11 | 17325
PC's Software & Hardware | 1600 | 11 | 17600
VoIP handset | 415 | 11 | 4565
Printer | 4325 | 1 | 4325
Ubiquiti wireless access points | 260 | 2 | 520
Cat 6e cable | 300 | 1 | 300
Ciena 5150 cable | 2145 | 1 | 2145
Furniture Total |  |  | 46780